## Project Export
Title | URL | Assignees | Status | Iteration | Labels | Linked pull requests | Estimate | Milestone
Price comparison | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/1 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Comparison view design/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/2 | udit710 | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Item Checkout | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/3 | ra5h1k | Done | Iteration | Type: Story |  | 1 | Milestone 1
Search Items | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/13 | IbrahimAshhab | Done | Iteration | Type: Story |  | 1 | Milestone 1
Product Detail | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/7 | ra5h1k | Done | Iteration | Type: Story |  | 1 | Milestone 1
Saved Items design/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/8 | udit710 | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Item Checkout/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/10 | ra5h1k | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Price Comparison | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/9 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Product Detail/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/11 | ra5h1k | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Architecture | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/14 | AbhijeetK520 | Done | Iteration | Type: Task |  | 1 | Milestone 1
Search Items API for search button | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/15 | IbrahimAshhab | Done | Iteration | Area: Backend |  | 7 | Milestone 1
Navigation Bar | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/16 | IbrahimAshhab | Done | Iteration | Area: Frontend |  | 1 | Milestone 1
Delivery options | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/19 | IbrahimAshhab | Done | Iteration | Type: Story |  | 1 | Milestone 1
Discount Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/24 | AbhijeetK520 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Notifications and Alerts | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/21 | AbhijeetK520 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Price Cmparision | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/25 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Saved Items | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/26 | udit710 | Done | Iteration | Type: Task |  | 1 | Milestone 1
Design the database schema. | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/37 | AbhijeetK520 | Done | Iteration | Area: Backend |  | 1 | Milestone 1
Saved Items List | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/6 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Home page Wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/12 | Vidyut03 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Category Selection Wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/18 | Vidyut03 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Home Page Story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/20 | Vidyut03 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Selection | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/17 | Vidyut03 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Notification Tab | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/22 | AbhijeetK520 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Saved Items List | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/23 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Home Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/29 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/30 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/31 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Product Details Section | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/32 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Product Details Section | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/33 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Filter Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/34 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Filter Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/35 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Item Checkout Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/36 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Request data from product api in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/76 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Use Product API to show product details in product page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/60 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 10 | Milestone 2
API Endpoint to get filtered products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/57 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/119 | 7 | Milestone 2
Request data from review api in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/75 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Convert frontend to create-react-app project | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/38 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/39 | 6 | Milestone 2
Navbar | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/5 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/40 | 6 | Milestone 2
Search Results page implementation | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/42 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Product Detail Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/41 | udit710 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Set up the development environment. | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/27 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task |  | 3 | Milestone 2
Setup API Endpoints to get list of all products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/56 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 7 | Milestone 2
Setup github workflow | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/55 | AbhijeetK520 | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/49, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/53 | 2 | Milestone 2
API Endpoint to update products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/58 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 8 | Milestone 2
API Endpoint to insert products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/59 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 8 | Milestone 2
Add Routing for Search Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/62 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/47, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Add Routing for Home Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/64 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/51, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/54 | 6 | Milestone 2
Write tests for Review API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/72 | Vidyut03 | Done | Iteration 3 | Area: Backend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86 | 4 | Milestone 2
API Endpoints to get user's orders | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/68 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/91 | 7 | Milestone 2
API Endpoints to get product reviews | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/69 | Vidyut03 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86 | 7 | Milestone 2
API Endpoint to get user details | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/70 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/111 | 3 | Milestone 2
Show offers based on discounts and categories in homepage | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/116 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/138 | 6 | Milestone 2
Frontend testing for search results page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/87 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/95 | 3 | Milestone 2
Test Cases for Orders API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/90 | udit710 | Done | Iteration 3 | Area: Backend, Testing |  | 4 | Milestone 2
Frontend tests for product detail page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/96 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97 | 3 | Milestone 2
User login page wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/79 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task |  | 1 | Milestone 2
User sign up page wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/80 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task |  | 1 | Milestone 2
User login page story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/77 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Story |  | 1 | Milestone 2
User sign up page story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/78 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Story |  | 1 | Milestone 2
Fix footer placement frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/85 | IbrahimAshhab | Done | Iteration 3 | Area: Frontend, Type: Bug | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/50, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/74, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/107 | 6 | Milestone 2
Update Product Details in Database to store discounts %, total price and discounted price | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/66 | IbrahimAshhab | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/112 | 9 | Milestone 2
Test Cases for User API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/113 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/115 | 3 | Milestone 2
Use Search API to show filtered product in search page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/61 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Add Category field to data model | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/117 | ra5h1k | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/122, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/123 | 6 | Milestone 2
Add Routing for Product Details Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/63 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/137 | 6 | Milestone 2
Add Product Review component to Product Details page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/120 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/124 | 6 | Milestone 2
Implement Search results data in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/128 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Fix productDeatils test frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/130 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing, Type: Bug | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/134 | 3 | Milestone 2
Pending Meeting minutes for August | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/131 | udit710 | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/133 | 2 | Milestone 2
Meeting minutes for September | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/132 | IbrahimAshhab | Done | Iteration 3 | Type: Task |  | 2 | Milestone 2
Meeting minutes for September week 2 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/143 | IbrahimAshhab | Done | Iteration 3 | Type: Task |  | 2 | Milestone 2
Update Transaction_Item table to contain product details id | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/67 | ra5h1k | Done | Iteration 3 | Area: Backend, Type: Task |  | 2 | Milestone 2
Finish backend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/141 | Vidyut03 | Done | Iteration 3 | Area: Backend, Testing, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/142 | 5 | Milestone 2
Fix Offers | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/144 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Bug, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/149, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/151 | 2 | Milestone 2
Meeting Minutes Week 1 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/146 | ra5h1k | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/153 | 2 | Milestone 2
Make Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/98 | IbrahimAshhab | Backlog | Iteration 4 | Area: Backend, Type: Task |  | 8 | Milestone 3
Connect Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/28 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 6 | Milestone 3
Test notification frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/100 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Test navbar frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/101 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Request data from backend api for cart | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/82 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Test cart items api | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/84 | Vidyut03 | Backlog | Iteration 4 | Area: Backend, Testing, Type: Task |  | 4 | Milestone 3
Implement saved_item/cart page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/81 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Implement cart items api | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/83 | Vidyut03 | Backlog | Iteration 4 | Area: Backend, Type: Task |  | 8 | Milestone 3
Test frontend cart page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/102 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Login Page Frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/103 |  | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Login page frontend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/104 |  | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Signup page frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/105 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Signup page frontend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/106 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Update notification frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/99 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Test Cases for Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/114 | IbrahimAshhab | Backlog | Iteration 4 | Area: Backend, Testing |  | 4 | Milestone 3

## Milestone 1
Title | URL | Assignees | Status | Iteration | Labels | Linked pull requests | Estimate | Milestone
Price comparison | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/1 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Comparison view design/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/2 | udit710 | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Item Checkout | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/3 | ra5h1k | Done | Iteration | Type: Story |  | 1 | Milestone 1
Search Items | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/13 | IbrahimAshhab | Done | Iteration | Type: Story |  | 1 | Milestone 1
Product Detail | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/7 | ra5h1k | Done | Iteration | Type: Story |  | 1 | Milestone 1
Saved Items design/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/8 | udit710 | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Item Checkout/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/10 | ra5h1k | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Price Comparison | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/9 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Product Detail/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/11 | ra5h1k | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Architecture | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/14 | AbhijeetK520 | Done | Iteration | Type: Task |  | 1 | Milestone 1
Search Items API for search button | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/15 | IbrahimAshhab | Done | Iteration | Area: Backend |  | 7 | Milestone 1
Navigation Bar | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/16 | IbrahimAshhab | Done | Iteration | Area: Frontend |  | 1 | Milestone 1
Delivery options | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/19 | IbrahimAshhab | Done | Iteration | Type: Story |  | 1 | Milestone 1
Discount Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/24 | AbhijeetK520 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Notifications and Alerts | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/21 | AbhijeetK520 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Price Cmparision | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/25 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Saved Items | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/26 | udit710 | Done | Iteration | Type: Task |  | 1 | Milestone 1
Design the database schema. | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/37 | AbhijeetK520 | Done | Iteration | Area: Backend |  | 1 | Milestone 1
Saved Items List | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/6 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Home page Wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/12 | Vidyut03 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Category Selection Wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/18 | Vidyut03 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Home Page Story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/20 | Vidyut03 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Selection | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/17 | Vidyut03 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Notification Tab | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/22 | AbhijeetK520 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Saved Items List | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/23 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Home Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/29 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/30 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/31 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Product Details Section | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/32 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Product Details Section | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/33 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Filter Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/34 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Filter Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/35 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Item Checkout Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/36 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Request data from product api in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/76 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Use Product API to show product details in product page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/60 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 10 | Milestone 2
API Endpoint to get filtered products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/57 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/119 | 7 | Milestone 2
Request data from review api in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/75 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Convert frontend to create-react-app project | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/38 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/39 | 6 | Milestone 2
Navbar | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/5 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/40 | 6 | Milestone 2
Search Results page implementation | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/42 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Product Detail Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/41 | udit710 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Set up the development environment. | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/27 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task |  | 3 | Milestone 2
Setup API Endpoints to get list of all products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/56 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 7 | Milestone 2
Setup github workflow | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/55 | AbhijeetK520 | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/49, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/53 | 2 | Milestone 2
API Endpoint to update products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/58 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 8 | Milestone 2
API Endpoint to insert products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/59 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 8 | Milestone 2
Add Routing for Search Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/62 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/47, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Add Routing for Home Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/64 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/51, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/54 | 6 | Milestone 2
Write tests for Review API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/72 | Vidyut03 | Done | Iteration 3 | Area: Backend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86 | 4 | Milestone 2
API Endpoints to get user's orders | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/68 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/91 | 7 | Milestone 2
API Endpoints to get product reviews | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/69 | Vidyut03 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86 | 7 | Milestone 2
API Endpoint to get user details | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/70 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/111 | 3 | Milestone 2
Show offers based on discounts and categories in homepage | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/116 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/138 | 6 | Milestone 2
Frontend testing for search results page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/87 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/95 | 3 | Milestone 2
Test Cases for Orders API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/90 | udit710 | Done | Iteration 3 | Area: Backend, Testing |  | 4 | Milestone 2
Frontend tests for product detail page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/96 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97 | 3 | Milestone 2
User login page wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/79 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task |  | 1 | Milestone 2
User sign up page wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/80 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task |  | 1 | Milestone 2
User login page story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/77 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Story |  | 1 | Milestone 2
User sign up page story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/78 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Story |  | 1 | Milestone 2
Fix footer placement frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/85 | IbrahimAshhab | Done | Iteration 3 | Area: Frontend, Type: Bug | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/50, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/74, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/107 | 6 | Milestone 2
Update Product Details in Database to store discounts %, total price and discounted price | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/66 | IbrahimAshhab | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/112 | 9 | Milestone 2
Test Cases for User API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/113 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/115 | 3 | Milestone 2
Use Search API to show filtered product in search page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/61 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Add Category field to data model | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/117 | ra5h1k | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/122, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/123 | 6 | Milestone 2
Add Routing for Product Details Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/63 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/137 | 6 | Milestone 2
Add Product Review component to Product Details page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/120 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/124 | 6 | Milestone 2
Implement Search results data in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/128 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Fix productDeatils test frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/130 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing, Type: Bug | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/134 | 3 | Milestone 2
Pending Meeting minutes for August | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/131 | udit710 | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/133 | 2 | Milestone 2
Meeting minutes for September | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/132 | IbrahimAshhab | Done | Iteration 3 | Type: Task |  | 2 | Milestone 2
Meeting minutes for September week 2 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/143 | IbrahimAshhab | Done | Iteration 3 | Type: Task |  | 2 | Milestone 2
Update Transaction_Item table to contain product details id | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/67 | ra5h1k | Done | Iteration 3 | Area: Backend, Type: Task |  | 2 | Milestone 2
Finish backend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/141 | Vidyut03 | Done | Iteration 3 | Area: Backend, Testing, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/142 | 5 | Milestone 2
Fix Offers | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/144 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Bug, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/149, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/151 | 2 | Milestone 2
Meeting Minutes Week 1 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/146 | ra5h1k | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/153 | 2 | Milestone 2
Make Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/98 | IbrahimAshhab | Backlog | Iteration 4 | Area: Backend, Type: Task |  | 8 | Milestone 3
Connect Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/28 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 6 | Milestone 3
Test notification frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/100 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Test navbar frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/101 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Request data from backend api for cart | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/82 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Test cart items api | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/84 | Vidyut03 | Backlog | Iteration 4 | Area: Backend, Testing, Type: Task |  | 4 | Milestone 3
Implement saved_item/cart page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/81 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Implement cart items api | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/83 | Vidyut03 | Backlog | Iteration 4 | Area: Backend, Type: Task |  | 8 | Milestone 3
Test frontend cart page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/102 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Login Page Frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/103 |  | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Login page frontend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/104 |  | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Signup page frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/105 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Signup page frontend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/106 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Update notification frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/99 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Test Cases for Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/114 | IbrahimAshhab | Backlog | Iteration 4 | Area: Backend, Testing |  | 4 | Milestone 3

## Milestone 2
Title | URL | Assignees | Status | Iteration | Labels | Linked pull requests | Estimate | Milestone
Price comparison | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/1 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Comparison view design/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/2 | udit710 | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Item Checkout | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/3 | ra5h1k | Done | Iteration | Type: Story |  | 1 | Milestone 1
Search Items | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/13 | IbrahimAshhab | Done | Iteration | Type: Story |  | 1 | Milestone 1
Product Detail | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/7 | ra5h1k | Done | Iteration | Type: Story |  | 1 | Milestone 1
Saved Items design/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/8 | udit710 | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Item Checkout/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/10 | ra5h1k | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Price Comparison | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/9 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Product Detail/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/11 | ra5h1k | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Architecture | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/14 | AbhijeetK520 | Done | Iteration | Type: Task |  | 1 | Milestone 1
Search Items API for search button | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/15 | IbrahimAshhab | Done | Iteration | Area: Backend |  | 7 | Milestone 1
Navigation Bar | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/16 | IbrahimAshhab | Done | Iteration | Area: Frontend |  | 1 | Milestone 1
Delivery options | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/19 | IbrahimAshhab | Done | Iteration | Type: Story |  | 1 | Milestone 1
Discount Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/24 | AbhijeetK520 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Notifications and Alerts | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/21 | AbhijeetK520 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Price Cmparision | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/25 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Saved Items | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/26 | udit710 | Done | Iteration | Type: Task |  | 1 | Milestone 1
Design the database schema. | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/37 | AbhijeetK520 | Done | Iteration | Area: Backend |  | 1 | Milestone 1
Saved Items List | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/6 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Home page Wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/12 | Vidyut03 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Category Selection Wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/18 | Vidyut03 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Home Page Story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/20 | Vidyut03 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Selection | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/17 | Vidyut03 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Notification Tab | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/22 | AbhijeetK520 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Saved Items List | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/23 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Home Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/29 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/30 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/31 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Product Details Section | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/32 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Product Details Section | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/33 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Filter Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/34 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Filter Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/35 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Item Checkout Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/36 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Request data from product api in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/76 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Use Product API to show product details in product page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/60 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 10 | Milestone 2
API Endpoint to get filtered products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/57 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/119 | 7 | Milestone 2
Request data from review api in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/75 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Convert frontend to create-react-app project | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/38 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/39 | 6 | Milestone 2
Navbar | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/5 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/40 | 6 | Milestone 2
Search Results page implementation | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/42 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Product Detail Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/41 | udit710 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Set up the development environment. | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/27 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task |  | 3 | Milestone 2
Setup API Endpoints to get list of all products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/56 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 7 | Milestone 2
Setup github workflow | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/55 | AbhijeetK520 | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/49, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/53 | 2 | Milestone 2
API Endpoint to update products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/58 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 8 | Milestone 2
API Endpoint to insert products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/59 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 8 | Milestone 2
Add Routing for Search Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/62 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/47, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Add Routing for Home Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/64 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/51, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/54 | 6 | Milestone 2
Write tests for Review API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/72 | Vidyut03 | Done | Iteration 3 | Area: Backend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86 | 4 | Milestone 2
API Endpoints to get user's orders | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/68 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/91 | 7 | Milestone 2
API Endpoints to get product reviews | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/69 | Vidyut03 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86 | 7 | Milestone 2
API Endpoint to get user details | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/70 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/111 | 3 | Milestone 2
Show offers based on discounts and categories in homepage | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/116 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/138 | 6 | Milestone 2
Frontend testing for search results page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/87 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/95 | 3 | Milestone 2
Test Cases for Orders API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/90 | udit710 | Done | Iteration 3 | Area: Backend, Testing |  | 4 | Milestone 2
Frontend tests for product detail page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/96 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97 | 3 | Milestone 2
User login page wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/79 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task |  | 1 | Milestone 2
User sign up page wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/80 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task |  | 1 | Milestone 2
User login page story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/77 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Story |  | 1 | Milestone 2
User sign up page story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/78 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Story |  | 1 | Milestone 2
Fix footer placement frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/85 | IbrahimAshhab | Done | Iteration 3 | Area: Frontend, Type: Bug | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/50, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/74, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/107 | 6 | Milestone 2
Update Product Details in Database to store discounts %, total price and discounted price | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/66 | IbrahimAshhab | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/112 | 9 | Milestone 2
Test Cases for User API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/113 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/115 | 3 | Milestone 2
Use Search API to show filtered product in search page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/61 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Add Category field to data model | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/117 | ra5h1k | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/122, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/123 | 6 | Milestone 2
Add Routing for Product Details Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/63 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/137 | 6 | Milestone 2
Add Product Review component to Product Details page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/120 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/124 | 6 | Milestone 2
Implement Search results data in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/128 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Fix productDeatils test frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/130 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing, Type: Bug | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/134 | 3 | Milestone 2
Pending Meeting minutes for August | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/131 | udit710 | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/133 | 2 | Milestone 2
Meeting minutes for September | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/132 | IbrahimAshhab | Done | Iteration 3 | Type: Task |  | 2 | Milestone 2
Meeting minutes for September week 2 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/143 | IbrahimAshhab | Done | Iteration 3 | Type: Task |  | 2 | Milestone 2
Update Transaction_Item table to contain product details id | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/67 | ra5h1k | Done | Iteration 3 | Area: Backend, Type: Task |  | 2 | Milestone 2
Finish backend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/141 | Vidyut03 | Done | Iteration 3 | Area: Backend, Testing, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/142 | 5 | Milestone 2
Fix Offers | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/144 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Bug, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/149, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/151 | 2 | Milestone 2
Meeting Minutes Week 1 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/146 | ra5h1k | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/153 | 2 | Milestone 2
Make Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/98 | IbrahimAshhab | Backlog | Iteration 4 | Area: Backend, Type: Task |  | 8 | Milestone 3
Connect Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/28 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 6 | Milestone 3
Test notification frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/100 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Test navbar frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/101 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Request data from backend api for cart | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/82 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Test cart items api | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/84 | Vidyut03 | Backlog | Iteration 4 | Area: Backend, Testing, Type: Task |  | 4 | Milestone 3
Implement saved_item/cart page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/81 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Implement cart items api | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/83 | Vidyut03 | Backlog | Iteration 4 | Area: Backend, Type: Task |  | 8 | Milestone 3
Test frontend cart page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/102 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Login Page Frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/103 |  | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Login page frontend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/104 |  | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Signup page frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/105 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Signup page frontend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/106 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Update notification frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/99 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Test Cases for Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/114 | IbrahimAshhab | Backlog | Iteration 4 | Area: Backend, Testing |  | 4 | Milestone 3

## Milestone 3 (Backlog)
Title | URL | Assignees | Status | Iteration | Labels | Linked pull requests | Estimate | Milestone
Price comparison | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/1 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Comparison view design/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/2 | udit710 | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Item Checkout | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/3 | ra5h1k | Done | Iteration | Type: Story |  | 1 | Milestone 1
Search Items | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/13 | IbrahimAshhab | Done | Iteration | Type: Story |  | 1 | Milestone 1
Product Detail | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/7 | ra5h1k | Done | Iteration | Type: Story |  | 1 | Milestone 1
Saved Items design/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/8 | udit710 | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Item Checkout/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/10 | ra5h1k | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Price Comparison | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/9 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Product Detail/wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/11 | ra5h1k | Done | Iteration | Area: Frontend, Type: Task |  | 1 | Milestone 1
Architecture | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/14 | AbhijeetK520 | Done | Iteration | Type: Task |  | 1 | Milestone 1
Search Items API for search button | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/15 | IbrahimAshhab | Done | Iteration | Area: Backend |  | 7 | Milestone 1
Navigation Bar | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/16 | IbrahimAshhab | Done | Iteration | Area: Frontend |  | 1 | Milestone 1
Delivery options | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/19 | IbrahimAshhab | Done | Iteration | Type: Story |  | 1 | Milestone 1
Discount Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/24 | AbhijeetK520 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Notifications and Alerts | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/21 | AbhijeetK520 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Price Cmparision | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/25 | udit710 | Done | Iteration | Type: Story |  | 1 | Milestone 1
Saved Items | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/26 | udit710 | Done | Iteration | Type: Task |  | 1 | Milestone 1
Design the database schema. | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/37 | AbhijeetK520 | Done | Iteration | Area: Backend |  | 1 | Milestone 1
Saved Items List | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/6 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Home page Wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/12 | Vidyut03 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Category Selection Wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/18 | Vidyut03 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Home Page Story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/20 | Vidyut03 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Selection | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/17 | Vidyut03 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Notification Tab | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/22 | AbhijeetK520 | Done | Iteration 2 | Area: Frontend, Type: Task |  | 1 | Milestone 1
Saved Items List | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/23 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Home Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/29 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/30 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Category Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/31 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Product Details Section | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/32 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Product Details Section | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/33 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Filter Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/34 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Filter Dropdown | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/35 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Item Checkout Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/36 | udit710 | Done | Iteration 2 | Type: Story |  | 1 | Milestone 1
Request data from product api in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/76 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Use Product API to show product details in product page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/60 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 10 | Milestone 2
API Endpoint to get filtered products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/57 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/119 | 7 | Milestone 2
Request data from review api in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/75 | AbhijeetK520 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Convert frontend to create-react-app project | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/38 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/39 | 6 | Milestone 2
Navbar | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/5 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/40 | 6 | Milestone 2
Search Results page implementation | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/42 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Product Detail Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/41 | udit710 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/108 | 6 | Milestone 2
Set up the development environment. | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/27 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task |  | 3 | Milestone 2
Setup API Endpoints to get list of all products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/56 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 7 | Milestone 2
Setup github workflow | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/55 | AbhijeetK520 | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/49, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/53 | 2 | Milestone 2
API Endpoint to update products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/58 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 8 | Milestone 2
API Endpoint to insert products | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/59 | AbhijeetK520 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/48 | 8 | Milestone 2
Add Routing for Search Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/62 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/47, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/118, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Add Routing for Home Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/64 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/51, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/54 | 6 | Milestone 2
Write tests for Review API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/72 | Vidyut03 | Done | Iteration 3 | Area: Backend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86 | 4 | Milestone 2
API Endpoints to get user's orders | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/68 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/91 | 7 | Milestone 2
API Endpoints to get product reviews | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/69 | Vidyut03 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/73, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/86 | 7 | Milestone 2
API Endpoint to get user details | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/70 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/111 | 3 | Milestone 2
Show offers based on discounts and categories in homepage | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/116 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/138 | 6 | Milestone 2
Frontend testing for search results page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/87 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/95 | 3 | Milestone 2
Test Cases for Orders API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/90 | udit710 | Done | Iteration 3 | Area: Backend, Testing |  | 4 | Milestone 2
Frontend tests for product detail page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/96 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/97 | 3 | Milestone 2
User login page wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/79 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task |  | 1 | Milestone 2
User sign up page wireframe | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/80 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task |  | 1 | Milestone 2
User login page story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/77 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Story |  | 1 | Milestone 2
User sign up page story | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/78 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Story |  | 1 | Milestone 2
Fix footer placement frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/85 | IbrahimAshhab | Done | Iteration 3 | Area: Frontend, Type: Bug | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/50, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/74, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/107 | 6 | Milestone 2
Update Product Details in Database to store discounts %, total price and discounted price | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/66 | IbrahimAshhab | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/112 | 9 | Milestone 2
Test Cases for User API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/113 | udit710 | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/115 | 3 | Milestone 2
Use Search API to show filtered product in search page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/61 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Add Category field to data model | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/117 | ra5h1k | Done | Iteration 3 | Area: Backend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/122, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/123 | 6 | Milestone 2
Add Routing for Product Details Page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/63 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/137 | 6 | Milestone 2
Add Product Review component to Product Details page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/120 | ra5h1k | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/124 | 6 | Milestone 2
Implement Search results data in frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/128 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/129 | 6 | Milestone 2
Fix productDeatils test frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/130 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Testing, Type: Bug | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/134 | 3 | Milestone 2
Pending Meeting minutes for August | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/131 | udit710 | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/133 | 2 | Milestone 2
Meeting minutes for September | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/132 | IbrahimAshhab | Done | Iteration 3 | Type: Task |  | 2 | Milestone 2
Meeting minutes for September week 2 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/143 | IbrahimAshhab | Done | Iteration 3 | Type: Task |  | 2 | Milestone 2
Update Transaction_Item table to contain product details id | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/67 | ra5h1k | Done | Iteration 3 | Area: Backend, Type: Task |  | 2 | Milestone 2
Finish backend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/141 | Vidyut03 | Done | Iteration 3 | Area: Backend, Testing, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/142 | 5 | Milestone 2
Fix Offers | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/144 | Vidyut03 | Done | Iteration 3 | Area: Frontend, Type: Bug, Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/149, https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/151 | 2 | Milestone 2
Meeting Minutes Week 1 | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/146 | ra5h1k | Done | Iteration 3 | Type: Task | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/pull/153 | 2 | Milestone 2
Make Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/98 | IbrahimAshhab | Backlog | Iteration 4 | Area: Backend, Type: Task |  | 8 | Milestone 3
Connect Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/28 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 6 | Milestone 3
Test notification frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/100 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Test navbar frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/101 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Request data from backend api for cart | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/82 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Test cart items api | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/84 | Vidyut03 | Backlog | Iteration 4 | Area: Backend, Testing, Type: Task |  | 4 | Milestone 3
Implement saved_item/cart page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/81 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Implement cart items api | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/83 | Vidyut03 | Backlog | Iteration 4 | Area: Backend, Type: Task |  | 8 | Milestone 3
Test frontend cart page | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/102 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Login Page Frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/103 |  | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Login page frontend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/104 |  | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Signup page frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/105 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Signup page frontend tests | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/106 | Vidyut03 | Backlog | Iteration 4 | Area: Frontend, Testing |  | 3 | Milestone 3
Update notification frontend | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/99 | AbhijeetK520 | Backlog | Iteration 4 | Area: Frontend, Type: Task |  | 5 | Milestone 3
Test Cases for Notification API | https://github.com/cosc2299-sept-2023/team-project-group-p02-07/issues/114 | IbrahimAshhab | Backlog | Iteration 4 | Area: Backend, Testing |  | 4 | Milestone 3